## Quotation
Delhi PS-CRM — Project Cost Quotation
AI-Powered WhatsApp Civic Complaint Management System
Team: Delhi PS-CRM ¦ Document: Cost Quotation v1.0 ¦ Excluding all applicable taxes
SECTION 1 — PROJECT OVERVIEW HEADER
Target Scale: |  | 1,00,000 complaints/month across 272 Delhi wards
Technology Stack: |  | FastAPI, Gemini 2.0 Flash, Gradient Boosting ML, Azure Cloud, WhatsApp Business API, SendGrid
Deployment Timeline: |  | 2 months
Languages Supported: |  | Hindi and English
SECTION 2 — PHASE-WISE COST SUMMARY
Phase | Duration | Description | Key Activities | Est. Complaints/Month | Phase Cost (Rs.)
Phase 1 | Weeks 1-2 | Development and Testing | Backend complete, WhatsApp bot on test numbers, ML model integrated, staging environment, internal QA | 0 | 115000
Phase 2 | Weeks 3-4 | Pilot Deployment | Live in 5 Delhi wards, real citizen complaints, bug fixes, officer onboarding | 1,000 | 95940
Phase 3 | Weeks 5-6 | Partial Rollout | Expand to 50 wards, department routing live, ML escalation running on real data | 20,000 | 55620
Phase 4 | Weeks 7-8 | Full Delhi Deployment | All 272 wards live, 1,00,000 complaints/month, full system operational | 1,00,000 | 156940
Phase 5 | Month 3 onwards | Steady State Operations | Handed to Delhi government IT team. Maintenance only, quarterly ML retraining | 1,00,000 | 107250
Total Project Cost Phases 1-4: Rs. 4,23,500
Annual Maintenance from Month 3: Rs. 12,87,000
SECTION 3 — DETAILED LINE-ITEM BREAKDOWN
Phase | Category | Item | Specifications and Details | Quantity / Duration | Unit Cost (Rs.) | Total Cost (Rs.) | Notes
Phase 1 total: Rs. 1,15,000 | [5 empty] | 115000
Phase 1 | Team | Student Developer Stipends | 5 team members: backend, ML integration, architecture, testing, DevOps | 5 x 0.5 month | 18,000/member/month | 45000 | Half month stipend weeks 1-2
Phase 1 | Infrastructure | Azure Container Apps Staging | Staging FastAPI backend for internal testing | 0.5 month | 4,000 | 2000 | Minimal staging instance
Phase 1 | Infrastructure | Azure Database for PostgreSQL Staging | Managed database for development and testing | 0.5 month | 2,500 | 1250 | Burstable B1ms tier
Phase 1 | Testing | WhatsApp API Sandbox | Meta WhatsApp Business API test numbers and sandbox | One-time | 5,000 | 5000 | Test message costs
Phase 1 | Testing | API Integration Testing | Gemini API test calls, SendGrid test emails, staging instance | One-time | 4,000 | 4000 | All third-party API test costs
Phase 2 total: Rs. 95,940 | [5 empty] | 95940
Phase 2 | Team | Student Developer Stipends | 5 members during pilot: monitoring, bug fixes, officer onboarding | 5 x 0.5 month | 18,000/member/month | 45000 | Half month stipend weeks 3-4
Phase 2 | Infrastructure | Azure Container Apps | Live backend for 5-ward pilot | 0.5 month | 4,000 | 2000 | Small instance
Phase 2 | Infrastructure | Azure Database for PostgreSQL | Live database for pilot | 0.5 month | 2,500 | 1250 | Burstable tier
Phase 2 | Infrastructure | Azure Blob Storage | Photo evidence for pilot complaints | 0.5 month | 500 | 250 | Minimal at 1K complaints
Phase 2 | AI and ML | Gemini 2.0 Flash API | AI classification for 1,000 pilot complaints | 1,000 calls | 0.40/call | 400 | Per-token billing
Phase 2 | Communication | WhatsApp Business API | Live messaging for 5-ward pilot | 1,000 conversations | 0.47/conversation | 470 | Per conversation
Phase 2 | Communication | SendGrid | Department notification emails | 1,000 emails | 0.10/email | 100 | Free tier covers this
Phase 3 total: Rs. 55,620 | [5 empty] | 55620
Phase 3 | Infrastructure | Azure Container Apps | Scaled backend for 50 wards | 0.5 month | 8,000 | 4000 | Medium instance
Phase 3 | Infrastructure | Azure Database for PostgreSQL Flexible | Production-grade database with backups | 0.5 month | 5,000 | 2500 | General Purpose tier
Phase 3 | Infrastructure | Azure Blob Storage | 40GB photo storage at 20K complaints | 0.5 month | 1,500 | 750 | LRS redundancy
Phase 3 | Infrastructure | Azure Monitor | Observability and alerting | 0.5 month | 1,500 | 750 | Required for SLA
Phase 3 | Infrastructure | Azure Service Bus | Webhook event queuing at 20K/month | 0.5 month | 1,000 | 500 | Standard tier
Phase 3 | AI and ML | Gemini 2.0 Flash API | AI classification for 20,000 complaints | 20,000 calls | 0.40/call | 8000 | Hindi and English
Phase 3 | AI and ML | Azure Machine Learning | First retraining run on real pilot data | 1 run | 8,000 | 8000 | Gradient Boosting retraining
Phase 3 | Communication | WhatsApp Business API | Messaging for 50-ward citizens | 20,000 conversations | 0.47/conversation | 9400 | Scaling cost
Phase 3 | Communication | SendGrid | Department and HoD emails | 20,000 emails | 0.10/email | 2000 | Essentials plan
Phase 3 | Infrastructure | Azure Front Door CDN | Officer dashboard CDN, domain, SSL | 0.5 month | 1,500 | 750 | Dashboard goes live
Phase 4 total: Rs. 1,56,940 | [5 empty] | 156940
Phase 4 | Infrastructure | Azure Container Apps | Full-scale auto-scaling for 272 wards | 0.5 month | 15,000 | 7500 | Production with zone redundancy
Phase 4 | Infrastructure | Azure Database for PostgreSQL | High-availability production database with geo-redundant backups and Indian data residency compliance | 0.5 month | 12,000 | 6000 | Business Critical tier
Phase 4 | Infrastructure | Azure Blob Storage | 200GB photo storage at 1L complaints/month | 0.5 month | 4,000 | 2000 | GRS geo-redundant
Phase 4 | Infrastructure | Azure Monitor | Full production observability with custom dashboards | 0.5 month | 3,000 | 1500 | 90-day log retention
Phase 4 | Infrastructure | Azure Service Bus | Premium tier guaranteed delivery at 1L/month | 0.5 month | 2,000 | 1000 | Premium tier
Phase 4 | Infrastructure | Azure Front Door CDN | Full production CDN with WAF and DDoS protection | 0.5 month | 3,000 | 1500 | WAF enabled
Phase 4 | AI and ML | Gemini 2.0 Flash API | Full-scale classification at 1,00,000 complaints/month | 1,00,000 calls | 0.40/call | 40000 | Largest AI cost
Phase 4 | AI and ML | Azure Machine Learning | Second retraining on expanded real complaint dataset | 1 run | 8,000 | 8000 | Accuracy improves with real data
Phase 4 | Communication | WhatsApp Business API | Full Delhi citizen messaging at 1L conversations/month | 1,00,000 conversations | 0.47/conversation | 47000 | Peak communication cost
Phase 4 | Communication | SendGrid | Full department and HoD email volume | 1,00,000 emails | 0.10/email | 10000 | Pro plan
Phase 5 monthly recurring: Rs. 1,07,250/month | [5 empty] | 107250
Phase 5 | Infrastructure | Azure Container Apps | per month | 1 month | 15,000 | 15000 | Recurring
Phase 5 | Infrastructure | Azure Database for PostgreSQL | per month | 1 month | 12,000 | 12000 | Recurring
Phase 5 | Infrastructure | Azure Blob Storage | per month | 1 month | 4,000 | 4000 | Recurring
Phase 5 | Infrastructure | Azure Monitor | per month | 1 month | 3,000 | 3000 | Recurring
Phase 5 | Infrastructure | Azure Service Bus | per month | 1 month | 2,000 | 2000 | Recurring
Phase 5 | Infrastructure | Azure Front Door CDN | per month | 1 month | 3,000 | 3000 | Recurring
Phase 5 | AI and ML | Gemini 2.0 Flash API | per month | 1 month | 8,000 | 8000 | Recurring
Phase 5 | AI and ML | Azure Machine Learning | per month amortized | 1 month | 5,000 | 5000 | Quarterly retraining
Phase 5 | Communication | WhatsApp Business API | per month | 1 month | 47,000 | 47000 | Recurring
Phase 5 | Communication | SendGrid | per month | 1 month | 3,500 | 3500 | Recurring
Phase 5 | Infrastructure | Azure backup and compliance | per month | 1 month | 1,500 | 1500 | Recurring
Phase 5 | Infrastructure | Azure Monitor log analytics | per month | 1 month | 750 | 750 | Recurring
SECTION 4 — UNIT ECONOMICS
Unit Economics and Value Justification
Metric | Value
Total deployment cost Phases 1-4 | 423500
Annual steady state cost Year 2 | 1287000
Cost per ward per month at full scale | 393
Cost per complaint at full scale | 1.07
Citizens served estimate | 200000000
Cost per citizen per year | 0.64
Wards covered at full deployment | 272
Languages supported | Hindi and English
Complaints processed per year estimate | 1200000
Cost per complaint of Rs. 1.07 includes AI classification, WhatsApp messaging, cloud infrastructure, email notifications, and ML-based auto-escalation -- delivered at a fraction of the cost of traditional call-centre based grievance systems.