## Quotation
Delhi PS-CRM — Project Cost Quotation
AI-Powered WhatsApp Civic Complaint Management System
Team: 5Baddies ¦ Document: Cost Quotation v2.0 ¦ Excluding all applicable taxes ¦ All prices in INR
SECTION 1 — PROJECT OVERVIEW HEADER
Target Scale: |  | 1,00,000 complaints/month across 272 Delhi wards
Technology Stack: |  | FastAPI, Gemini 2.5 Flash-Lite, Gradient Boosting ML, Azure Cloud, WhatsApp Business API, SendGrid
Deployment Timeline: |  | 2 months
Languages Supported: |  | Hindi and English
SECTION 2 — PHASE-WISE COST SUMMARY
Phase | Duration | Description | Key Activities | Est. Complaints/Month | Phase Cost (Rs.)
Phase 1 | Weeks 1-2 | Development and Testing | Backend complete, WhatsApp bot on test numbers, ML model integrated, staging environment, internal QA | 0 | 60750
Phase 2 | Weeks 3-4 | Pilot Deployment | Live in 5 Delhi wards, real citizen complaints, bug fixes, officer onboarding | 1,000 | 51250
Phase 3 | Weeks 5-6 | Partial Rollout | Expand to 50 wards, department routing live, ML escalation running on real data | 20,000 | 68588
Phase 4 | Weeks 7-8 | Full Delhi Deployment | All 272 wards live, 75,000 complaints/month, full system operational | 75,000 | 83370
Phase 5 | Month 3 onwards | Steady State Operations | Handed to Delhi government IT team. Maintenance only, quarterly ML retraining | 1,00,000 | 58890
Total Project Cost Phases 1-4 |  |  |  |  | 263958
Annual Maintenance from Month 3 |  |  |  |  | 706680
SECTION 3 — DETAILED LINE-ITEM BREAKDOWN
Phase | Category | Item | Specifications and Details | Quantity / Duration | Unit Cost (Rs.) | Total Cost (Rs.) | Notes
Phase 1 | Team | Student Developer Stipends | 5 students × 2 weeks (0.5 month) @ Rs. 18,000/person/month | 5 | 9000 | 45000 | Rs. 18,000/person/month × 0.5 month × 5 students = Rs. 45,000
Phase 1 | Infrastructure | Azure Container Apps Staging | Staging FastAPI backend for internal testing | 0.5 | 4000 | 2000 | Minimal staging instance
Phase 1 | Infrastructure | Azure Database for PostgreSQL Staging | Managed database for development and testing | 0.5 | 2500 | 1250 | Burstable B1ms tier
Phase 1 | Testing | WhatsApp API Sandbox | Meta WhatsApp Business API test numbers and sandbox | 1 | 5000 | 5000 | Test message costs
Phase 1 | Testing | API Integration Testing | Gemini API test calls, SendGrid test emails, staging instance | 1 | 4000 | 4000 | All third-party API test costs
Phase 1 | Testing | Gemini Audio API Testing | Voice note transcription and classification testing via Gemini Audio API | 1 | 1000 | 1000 | Audio API test costs for voice complaints
Phase 1 | Contingency | Contingency Reserve | Buffer for unexpected API overages, infra spikes, or integration issues | 1 | 2500 | 2500 | ~5% of phase operational costs
Phase 1 Subtotal | [5 empty] | 60750
Phase 2 | Team | Student Developer Stipends | 5 students × 2 weeks (0.5 month) @ Rs. 18,000/person/month | 5 | 9000 | 45000 | Rs. 18,000/person/month × 0.5 month × 5 students = Rs. 45,000
Phase 2 | Infrastructure | Azure Container Apps | Live backend for 5-ward pilot | 0.5 | 4000 | 2000 | Small instance
Phase 2 | Infrastructure | Azure Database for PostgreSQL | Live database for pilot | 0.5 | 2500 | 1250 | Burstable tier
Phase 2 | Infrastructure | Azure Blob Storage | Photo evidence for pilot complaints | 0.5 | 500 | 250 | Minimal at 1K complaints
Phase 2 | AI and ML | Gemini 2.5 Flash-Lite API | AI classification for 1,000 pilot complaints | 1000 | 0.05 | 50 | $0.10/M input + $0.40/M output @ 84 INR/USD, 30% voice mix = Rs. 0.05/call
Phase 2 | Communication | WhatsApp Business API | Live messaging for 5-ward pilot | 1000 | 0.1 | 100 | Service convos FREE (citizen-initiated 24h window). Rs. 0.145/utility template × 2 notifs × 20% outside window = Rs. 0.058/complaint
Phase 2 | Communication | SendGrid | Department notification emails | 1 | 100 | 100 | Free tier covers 1K emails
Phase 2 | Contingency | Contingency Reserve | Buffer for unexpected API overages, infra spikes, or integration issues | 1 | 2500 | 2500 | ~5% of phase operational costs
Phase 2 Subtotal | [5 empty] | 51250
Phase 3 | Team | Student Developer Stipends | 5 students × 2 weeks (0.5 month) @ Rs. 18,000/person/month | 5 | 9000 | 45000 | Rs. 18,000/person/month × 0.5 month × 5 students = Rs. 45,000
Phase 3 | Infrastructure | Azure Container Apps | Scaled backend for 50 wards | 0.5 | 8000 | 4000 | Medium instance
Phase 3 | Infrastructure | Azure Database for PostgreSQL Flexible | Production-grade database with backups | 0.5 | 5000 | 2500 | General Purpose tier
Phase 3 | Infrastructure | Azure Blob Storage | 40GB photo storage at 20K complaints | 0.5 | 1500 | 750 | LRS redundancy
Phase 3 | Infrastructure | Azure Monitor | Observability and alerting | 0.5 | 1500 | 750 | Required for SLA
Phase 3 | Infrastructure | Azure Service Bus | Webhook event queuing at 20K/month | 0.5 | 1000 | 500 | Standard tier
Phase 3 | AI and ML | Gemini 2.5 Flash-Lite API | AI classification for 20,000 complaints | 20000 | 0.015 | 300 | Rs. 0.012/call avg with voice mix, rounded up
Phase 3 | AI and ML | Azure Machine Learning | First retraining run on real pilot data | 1 | 8000 | 8000 | Gradient Boosting retraining
Phase 3 | Communication | WhatsApp Business API | Messaging for 50-ward citizens | 20000 | 0.06 | 1200 | 2 utility templates × 20% outside 24h window × Rs. 0.145 = Rs. 0.058/complaint
Phase 3 | Communication | SendGrid Essentials 50K | $19.95/mo = Rs. 1,676/mo | 0.5 | 1676 | 838 | Essentials plan
Phase 3 | Infrastructure | Azure Front Door CDN | Officer dashboard CDN, domain, SSL | 0.5 | 1500 | 750 | Dashboard goes live
Phase 3 | Contingency | Contingency Reserve | Buffer for unexpected API overages, infra spikes, or integration issues | 1 | 4000 | 4000 | ~5% of phase operational costs
Phase 3 Subtotal | [5 empty] | 68588
Phase 4 | Team | Student Developer Stipends | 5 students × 2 weeks (0.5 month) @ Rs. 18,000/person/month | 5 | 9000 | 45000 | Rs. 18,000/person/month × 0.5 month × 5 students = Rs. 45,000
Phase 4 | Infrastructure | Azure Container Apps | Full-scale auto-scaling for 272 wards | 0.5 | 15000 | 7500 | Production with zone redundancy
Phase 4 | Infrastructure | Azure Database for PostgreSQL | High-availability production DB with geo-redundant backups and Indian data residency compliance | 0.5 | 12000 | 6000 | Business Critical tier
Phase 4 | Infrastructure | Azure Blob Storage | 200GB photo storage at 1L complaints/month | 0.5 | 4000 | 2000 | GRS geo-redundant
Phase 4 | Infrastructure | Azure Monitor | Full production observability with custom dashboards | 0.5 | 3000 | 1500 | 90-day log retention
Phase 4 | Infrastructure | Azure Service Bus | Premium tier guaranteed delivery at 1L/month | 0.5 | 2000 | 1000 | Premium tier
Phase 4 | Infrastructure | Azure Front Door CDN | Full production CDN with WAF and DDoS protection | 0.5 | 3000 | 1500 | WAF enabled
Phase 4 | AI and ML | Gemini 2.5 Flash-Lite API | Full-scale classification at 75,000 complaints/month | 75000 | 0.012 | 900 | Full scale with 30% voice mix
Phase 4 | AI and ML | Azure Machine Learning | Second retraining on expanded real complaint dataset | 1 | 8000 | 8000 | Accuracy improves with real data
Phase 4 | Communication | WhatsApp Business API | Full Delhi citizen messaging at 75K conversations/month | 75000 | 0.06 | 4500 | Peak communication cost
Phase 4 | Communication | SendGrid Essentials 100K | $34.95/mo = Rs. 2,940/mo | 0.5 | 2940 | 1470 | Pro plan
Phase 4 | Contingency | Contingency Reserve | Buffer for unexpected API overages, infra spikes, or integration issues | 1 | 4000 | 4000 | ~5% of phase operational costs
Phase 4 Subtotal | [5 empty] | 83370
Phase 5 | Infrastructure | Azure Container Apps | per month | 1 | 15000 | 15000 | Recurring
Phase 5 | Infrastructure | Azure Database for PostgreSQL | per month | 1 | 12000 | 12000 | Recurring
Phase 5 | Infrastructure | Azure Blob Storage | per month | 1 | 4000 | 4000 | Recurring
Phase 5 | Infrastructure | Azure Monitor | per month | 1 | 3000 | 3000 | Recurring
Phase 5 | Infrastructure | Azure Service Bus | per month | 1 | 2000 | 2000 | Recurring
Phase 5 | Infrastructure | Azure Front Door CDN | per month | 1 | 3000 | 3000 | Recurring
Phase 5 | AI and ML | Gemini 2.5 Flash-Lite API | per month | 1 | 1200 | 1200 | Recurring
Phase 5 | AI and ML | Azure Machine Learning | per month amortized | 1 | 5000 | 5000 | Quarterly retraining
Phase 5 | Communication | WhatsApp Business API | per month | 1 | 6000 | 6000 | Recurring
Phase 5 | Communication | SendGrid Essentials 100K | per month | 1 | 2940 | 2940 | Recurring
Phase 5 | Infrastructure | Azure backup and compliance | per month | 1 | 1500 | 1500 | Recurring
Phase 5 | Infrastructure | Azure Monitor log analytics | per month | 1 | 750 | 750 | Recurring
Phase 5 | Contingency | Contingency Reserve | Buffer for unexpected API overages, infra spikes, or integration issues | 1 | 2500 | 2500 | ~5% of phase operational costs
Phase 5 Subtotal | [5 empty] | 58890
SECTION 4 — UNIT ECONOMICS
Unit Economics and Value Justification
Metric | Value
Total deployment cost Phases 1-4 | 263958
Annual steady state cost Year 2 | 706680
Cost per ward per month at full scale | 216.5074
Cost per complaint at full scale | 0.5889
Citizens served estimate | 200000000
Cost per citizen per year | 0.0035334
Wards covered at full deployment | 272
Languages supported | Hindi and English
Complaints processed per year estimate | 1200000
Cost per complaint includes AI classification (with voice note support via Gemini 2.5 Flash-Lite), WhatsApp messaging, cloud infrastructure, email notifications, and ML-based auto-escalation — delivered at a fraction of the cost of traditional call-centre based grievance systems.